## Instructions
RISK MANAGEMENT LOG
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each risk identified, complete the following:
A | ID: A unique ID number used to identify the risk in the risk tracking log.
B | Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
C | Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
D | Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue.
E | Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
F | Risk Description: This column should be populated with a description of the risk.
G | Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
H | Risk Area: This column should be populated with the appropriate risk area.
I | Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
J | Trigger: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
K | Risk Response Strategy: This column should be populated with the preferred risk response strategy.
L | Response Strategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
M | Contingency Plan: This column should be populated with a description of the risk contingency plan.
Column | Instructions For Changing the Contents of Drop-Down Menus
C, D, H | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## Risk_Tracking_Log
RISK MANAGEMENT LOG | [7 empty] | RISK MANAGEMENT LOG
Project Name: |  |  | Illumination |  |  |  |  | Project Name: | Illumination
National Center: |  |  | IIT |  |  |  |  | National Center: | IIT
Project Manager Name: |  |  | Jakub Urbaniak |  |  |  |  | Project Manager Name: | Jakub Urbaniak
Project Description: |  |  | Create software that will be able to scan, scrape, and collect data from various sites. |  |  |  |  | Project Description: | Create software that will be able to scan, scrape, and collect data from various sites.
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
1 | Open | Medium | Medium | Yellow | If someone gets sick with COVID-19, they can get others sick. Also, can cause unfair workloads and further alienate workers or cause workers to leave. | Possible Outbreak of COVID-19. May hinder progress of team. | Schedule | Workings providing positive test results or being out of office sick for 72 hours. | Can't smell or taste, light headache, close contact with positive patients | Avoidance | Find way to work around person whose sick and if we have enough time, that person can return to their role | If bad enough. someone else would need to take over their responsibilities
2 | Open | Low | Low | Green | Lack of communication will increase the probability of miscommunication and misunderstandings of tasks and team objectives. | Creates misinformation and issues with performance. Can cause team to miss deadlines. | Project Management | Arguments, poor interpretation of verbal instructions, misdirection, miscommunication in task assignments | Bad group dynamic, no clear leader. Testing of requirements fail or a high percentage fail. People showing up unprepared to meetings or tasks. Occurence of micromanagement. | Acceptance | Ping them multiple times a day to get a response, on multiple platforms - Discord, email, etc. | Contacting the professor to tell them of these issues and hopefully resolve them that way
3 | Open | High | Low | Yellow | Not backing up data will increase probability of losing critical information and work that is important to completing project. | Loss of progress in project and any valuable information for project. Also can cause complete loss of entire project. | Data/Information | Loss of entire project, data corruption, data loss. | Not purchasing back up devices and not backing up data. | Contingency | Find backups on someones local machine | May need to restart project
4 | Open | Medium | Medium | Yellow | Failure or issues to integrate code will cause progress of project to slow down. | Will slow down the process of creating and implementing code. This will heavily slow down the progress of the team. | Project Management | Code failure, decrease in project progress | No updates in code for weeks will slow down the progress of project. | Transfer | Have group members constantly push code to GitHub | Group members may need to re-write code if its not pushed
5 | Open | Low | Medium | Green | Malfunctions of hardware or hardware breaking. Including driver issues, technical part breaking, or software updates causing issues. | Team will be unable to perform tasks and meet deadlines if hardware is not working properly or to maximum efficiency. | Technical Difficulty | Blue screen of death, malfunctions in applications, explosion | Outdated hardware, hardware overheating, hardware smoking | Contingency | Group members may need to hand off tasks if someone is having hardware problems | Buy new systems
6 | Open | Low | Low | Green | Users using different types of software or applications to complete work. | Will cause bugs in code integration or cause code not to work at all. | Reliability of Systems | Project corruption, library incompatibility | Syntax error, too many users working at the project at once, miscommunication | Acceptance | Use software that cooperates nicely | Use software that cooperates nicely
7 | Open | Medium | Medium | Yellow | If at any point one or multiple team members start to carry the workload of the team. This will create unfair workloads in the team. | Will cause burnout in one team member and will negativly impact the productivity of the team. | Project Management | Burnout, decrease in productivity, decrease in motivation and creativity | Exhaustion, over stressed | Transfer | Crossload work between other members | Force person working too much to stop
8 | Open | Medium | Medium | Yellow | Team members unable to be productive or struggling to complete tasks in a timely fashion. | Will slow down the process of meeting objectives and reaching project deadlines. | Surety Considerations | Late diliverables, not meeting deadlines | Procrastination | Contingency | Communicate with them and try to figure out a solutuion on work amounts | Contacting the professor to tell them of these issues and hopefully resolve them that way
9 | Open | High | Low | Yellow | Single point of failure happens If one person on the team is carrying the work load and are unable to continue working for any given reason. The rest of the team will be unable to complete tasks or continue the progress of the project. | Will cause the whole team to fail in meeting deadlines or completing projects | Surety Considerations | Work exhaustion, increase in stress, sabotage the project | Exhaustion, over stressed | Transfer | Send employee home for rest, crossload work between other members, rest between long period of work | Force person working too much to stop
10 | Open | High | Low | Yellow | The team unable to implement any of the requirements of the project. If the deliverables don’t meet customer expectations as set up in the contract. | Cant perform any tasks or complete any objectives. Can lead to overtime and burnout. Clients will refuse and not accept the project. Client will refuse to sign off on project and will end up in default of contract. | Future Procurements | Client not satisfied, termination of contract | Complaints from client, lack of progress in project, project not meeting the standards | Contingency | Re-tool deliverible to meet client needs | Re-make project from ground up or find new clients

## DropDown_Elements
Risk Area
Schedule
Initial Costs
Life-cycle Costs
Technical Obsolescence
Feasibility
Reliability of Systems
Dependencies/Interoperability
Surety Considerations
Future Procurements
Project Management
Overall Project Failure
Organizational/Change Management
Business
Data/Information
Technology
Strategic
Security
Privacy
Project Resources
Technical Difficulty