## Report
Project Illumination
Earned Value Analysis Report
					Period
	Prepared By:	Jakub Urbaniak
	Date:	03/22/22

	For Period:	3/22/2022-05/03-2022

Summary:
	All work calculated based off of hourly salary. 2400/2200/1400/1000 is basis for 40 hour week based on position on team.

Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS	Task Name	TBC	1	2	3	4	5	6
1.1	Project Manager	14400	2400	2400	2400	2400	2400	2400
1.2	Software Engineer	13200	2200	2200	2200	2200	2200	2200
1.3	Software Engineer	13200	2200	2200	2200	2200	2200	2200
1.4	Software Engineer	13200	2200	2200	2200	2200	2200	2200
1.5	Software Engineer	13200	2200	2200	2200	2200	2200	2200
1.6	Data Analyst	8400	1400	1400	1400	1400	1400	1400
1.7	Data Analyst	8400	1400	1400	1400	1400	1400	1400
1.8	Tester	6000	1000	1000	1000	1000	1000	1000
		0
		0
		0
		0
Insert new rows above this one
	Total Budgeted Cost	90000	15000	15000	15000	15000	15000	15000
		Cumulative Planned Value (PV)	15000	30000	45000	60000	75000	90000

Actual Cost and Earned Value
		Cumulative Actual Cost (AC)	12000	27000	42000	57000	65880	80880
		Cumulative Earned Value (EV)	1440	15120	52200	79320	88020	90000

Project Performance Metrics
		Cost Variance (CV = EV - AC)	-10560	-11880	10200	22320	22140	9120
		Schedule Variance (SV = EV - PV)	-13560	-14880	7200	19320	13020	0
		Cost Performance Index (CPI = EV/AC)	0.12	0.56	1.24	1.39	1.34	1.11
		Schedule Performance Index (SPI = EV/PV)	0.10	0.50	1.16	1.32	1.17	1.00
		Estimated Cost at Completion (EAC)	750000	160714	72414	64675	67362	80880

## EV
Earned Value Worksheet

This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP).					Earned Value Management Template
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.					© 2012 Vertex42 LLC
Enter the % Complete for each task to calculate the cumulative earned value.

Cumulative Earned Value (EV)
WBS	Task Name	TBC	Wk 1	Wk 2	Wk 3	Wk 4	Wk 5	Wk 6	Wk 7	Wk 8	Wk 9	Wk 10	Wk 11	Wk 12
1.1	Project Manager	14400	10%	50%	80%	100%	100%	100%
1.2	Software Engineer	13200	0%	15%	65%	90%	100%	100%
1.3	Software Engineer	13200	0%	15%	65%	90%	100%	100%
1.4	Software Engineer	13200	0%	15%	65%	90%	100%	100%
1.5	Software Engineer	13200	0%	15%	65%	90%	100%	100%
1.6	Data Analyst	8400	0%	0%	20%	75%	90%	100%
1.7	Data Analyst	8400	0%	0%	20%	75%	90%	100%
1.8	Tester	6000	0%	0%	50%	80%	95%	100%
-	-	0
-	-	0
-	-	0
-	-	0
Insert new rows above this one
		Cumulative EV	1440	15120	52200	79320	88020	90000	0	0	0	0	0	0

## AC
Actual Cost Worksheet

Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period.
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Transfer the Cumulative Actual Cost to the Report worksheet.

Actual Cost (AC) of Work Performed
WBS	Task Name		Wk 1	Wk 2	Wk 3	Wk 4	Wk 5	Wk 6	Wk 7	Wk 8	Wk 9	Wk 10	Wk 11	Wk 12
1.1	Project Manager		1920	2400	2400	2400	1440	2400
1.2	Software Engineer		1760	2200	2200	2200	1320	2200
1.3	Software Engineer		1760	2200	2200	2200	1320	2200
1.4	Software Engineer		1760	2200	2200	2200	1320	2200
1.5	Software Engineer		1760	2200	2200	2200	1320	2200
1.6	Data Analyst		1120	1400	1400	1400	840	1400
1.7	Data Analyst		1120	1400	1400	1400	840	1400
1.8	Tester		800	1000	1000	1000	480	1000
-	-
-	-
-	-
-	-
Insert new rows above this one
		Total Actual Cost	12000	15000	15000	15000	8880	15000	0	0	0	0	0	0

		Cumulative Actual Cost (AC)	12000	27000	42000	57000	65880	80880	80880	80880	80880	80880	80880	80880